## Hoja1
WEEK | Dates | Activities
Introductory module | May 6th - May 24th | -Immersion in the CHAOSS community -Understanding the contributing process of the community
1 | May 27th - May 31st | -Code_changes implementation and documentation -Proposals implementation and visualization
2 | June 3rd - June 7th | -Code_changes_lines implementation and documentation -Proposals Accepted implementation and documentation
3 | June 10 - June 14th | -Issues_New implementation and documentation -Issues_Closed implementation and documentation
4 | June 17th - June 21st | -Issues_Active implementation and documentation
5 | June 24th - June 28th | -GSoC evaluations -Contributors implementation and documentation -New Contributors implementation and documentation
6 | July 1st - July 5th | -New contributors of issues implementation and documentation -Open Issues implementation and documentation
7 | July 8th - July 12th | -New contributors of commits implementation and documentation -Closed Issues implementation and documentation
8 | July 15th - July 19th | -New contributors of code reviews implementation and documentation -Open Issue Age implementation and documentation
9 | July 22nd - July 26th | -GSoC evaluations -Pull Requests Merged/Closed (contribution acceptance) implementation and documentation
10 | July 29th - August 2nd | -Issue Response time implementation and documentation
11 | August 5th - August 9th | -Closed Issue Resolution Duration implementation and documentation
12 | August 12th - August 16th | -Issue Resolution Efficiency implementation and documentation
13 | August 19th - August 26th | -Final evaluations of the GSoC project